This is an example of what that departmental goal might look like:

| Example Department Goal |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective (goal) | Action Steps | Responsible Person | Measured by: | Due Date | Status |
| Assess Employee satisfaction and develop improvement plan to improve satisfaction score by 10%. | Survey employees for baseline score. | Susan Jones | Completion by due date. | March 1st | Completed |
|  | Review results and identify issues. | Joe Smith Susan Jones | Completion by due date. | April 15 | Completed |
|  | Facilitate focus group and drill down on identified issues. | Susan Jones | Completion by due date. | April 30 | Completed |
|  | Develop action plan based on feedback. | Susan Jones | Completion by due date. | May 15 | In Process |
|  | Implement action plan. | Joe Smith Susan Jones | Completion by due date. | June 30 | In Process |
|  | Re-survey employees. | Susan Jones | Completion by due date. | Jan 1st | In Process |
|  | Compare results. | Joe Smith Susan Jones | Improved results by 10% over baseline. | Feb 15 | In Process |
| This goal supports the strategic objective of reducing employee turnover rates by 50%, from 30% to 15%. |  |  |  |  |  |

Note:  This document is meant to serve as an example form and should not be construed as a legal document.  Please contact a legal professional for legal language for your specific organization.